| Parkside Academy Action Plan: PE 2025-26 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Focus | Objective (Intent) | Actions (Implementation) | Resources (Meeting time, cost, training, etc) | Time (Half term) | Outcome (Impact) |
| Planning | To design and implement a clearly sequenced PE curriculum, ensuring progressive skill development through partnership with the FET. | - Work collaboratively with the FET to review current PE provision and identify gaps and overlaps. - Map a whole-school PE curriculum that clearly shows progression of skills from EYFS to Year 6. - Ensure each unit builds on prior learning and prepares pupils for the next stage. - Align curriculum with national guidance and competition pathways. - Share curriculum overview with staff and provide guidance on progression expectations. | - FET curriculum expertise and planning support - National Curriculum PE guidance - Staff meeting time and planning documents - Progression maps and long-term planning templates - Use of FET-created Padlet | Assess Termly | - A coherent, progressive PE curriculum embedded across the school - Staff have a clear understanding of skills progression in PE - Pupils build confidence and competence as skills develop year on year - Improved consistency and quality of PE teaching across all classes |
| Assessment | To implement a standard, robust assessment and monitoring system | - Introduce a whole-school PE assessment framework aligned with the new curriculum. - Develop clear success criteria and age-related expectations for each unit. - Train staff on assessment methods, including observation and pupil self-assessment. - Monitor PE through lesson observations, pupil voice, and assessment data reviews. - Use assessment outcomes to inform planning and targeted support. | - PE assessment tracking system - Staff training time - Subject leader monitoring time | February 2026 | - Accurate assessment of pupil progress in PE - Teachers confident in assessing physical skills and knowledge - Identification of pupils needing additional support or challenge - Evidence to demonstrate impact of PE provision |
| Curriculum Enhancement | To expand the range of after-school clubs using local expertise in less accessible sports | - Audit current after-school provision and identify gaps in sporting opportunities. - Establish partnerships with local sports clubs, coaches, and organisations. - Introduce clubs offering sports pupils may not otherwise access (e.g. fencing, archery, martial arts). - Promote clubs to pupils and parents to encourage wide participation. - Monitor attendance and pupil engagement in clubs. | - Funding for external coaches - Local sports providers and community links - Timetabled after-school slots - Communication with parents and carers | Termly | - Increased participation in extracurricular sport - Broader sporting experiences for pupils - Improved physical confidence and enjoyment of physical activity - Strengthened links between school and local community sports providers |
| Resources | To invest in high-quality resources to effectively deliver the new curriculum | - Audit existing PE equipment to identify gaps and outdated resources. - Purchase high-quality, age-appropriate equipment aligned with curriculum needs. - Ensure sufficient quantities to enable full class participation. - Organise and label resources for ease of access and sustainability. - Review resource effectiveness annually. | - PE and Sport Premium funding - Equipment audit documentation | February 2026 | - Improved quality of PE lessons - Increased pupil engagement and active participation - Staff able to deliver lessons confidently and effectively - Resources that support skill progression across year groups |
| Outdoor Areas | To improve opportunities for play in outdoor areas | - Review current outdoor provision and identify areas for improvement. - Introduce structured and unstructured play equipment to encourage active play. - Develop playground zoning to support a variety of activities. - Train Play Leaders to encourage play at break and diner time. | - Outdoor play equipment - Playground markings and storage - Staff training for play facilitation - Pupil leadership materials | January 2026 | - Increased levels of physical activity during break and lunchtimes - Improved behaviour and engagement during outdoor play - Greater inclusivity in playground activities - Pupils developing social skills and teamwork through play |